## Dashboard
Project Status Dashboard
| Total Projects | % Completed | % Under Budget
| 12 | 16.67% | 91.67%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Data
Project Name | Department | Project Manager | Start Date | End Date | Days Remaining | Status | % Complete | Budget ($) | Actual Spend ($) | Variance $ | Budget Utilization % | Team Members | Priority
New Laptops for Staff | IT | Casey Morgan | 4565800% | 4596200% | 15 | In Progress | 50% | 500000 | 475000 | 25000 | 95% | 8 | Medium
CRM Roadmap | IT | Jordan Lee | 4571700% | 4602200% | 75 | In Progress | 65% | 120000 | 78000 | 42000 | 65% | 6 | High
Accreditation Standards Update | Education | Jordan Lee | 4580900% | 4600600% | 59 | In Progress | 60% | 50000 | 45000 | 5000 | 90% | 4 | Low
Learning Platform Redesign | Education | Casey Morgan | 4570300% | 4597600% | 29 | On Hold | 45% | 90000 | 55000 | 35000 | 61.11% | 4 | Medium
Member Journey Mapping & Onboarding Revamp | Member Engagement | Taylor Chen | 4569800% | 4603700% | 90 | On Hold | 35% | 125000 | 130000 | -5000 | 104% | 5 | High
Member Portal Enhancements | Member Engagement | Taylor Chen | 4574800% | 4596100% | 14 | In Progress | 80% | 75000 | 62000 | 13000 | 82.67% | 5 | High
Professional Standards Awareness Campaign | Professional Affairs | Jamie Brooks | 4573100% | 4599200% | 45 | In Progress | 55% | 30000 | 17000 | 13000 | 56.67% | 3 | Medium
Data Governance Audit | Professional Affairs | Riley Patel | 4567200% | 4591500% | -32 | Completed | 100% | 60000 | 59500 | 500 | 99.17% | 3 | Low
Historical Budget Archive Consolidation | Finance | Riley Patel | 4583800% | 4602200% | 75 | In Progress | 85% | 20000 | 10000 | 10000 | 50% | 2 | Medium
Finance Automation | Finance | Alex Rivera | 4578700% | 4600600% | 59 | In Progress | 50% | 110000 | 67000 | 43000 | 60.91% | 4 | High
Total Rewards & Compensation Structure Redesign | HR | Alex Rivera | 4568900% | 4605400% | 107 | In Progress | 65% | 650000 | 500000 | 150000 | 76.92% | 3 | High
Staff Training Program | HR | Jamie Brooks | 4568900% | 4589900% | -48 | Completed | 100% | 45000 | 44200 | 800 | 98.22% | 2 | Medium
Formulas:
Days Remaining = [End Date]-TODAY()

## Department Budget
Department | Sum of Budget ($) | Sum of Actual Spend ($)
Education | 140000 | 100000
Finance | 130000 | 77000
HR | 695000 | 544200
IT | 620000 | 553000
Member Engagement | 200000 | 192000
Professional Affairs | 90000 | 76500
Grand Total | 1875000 | 1542700

## Status
Count of Status | Status
Department | Completed | In Progress | On Hold | Grand Total
Education |  | 1 | 1 | 2
Finance |  | 2 |  | 2
HR | 1 | 1 |  | 2
IT |  | 2 |  | 2
Member Engagement |  | 1 | 1 | 2
Professional Affairs | 1 | 1 |  | 2
Grand Total | 2 | 8 | 2 | 12